## Title
Organisational Readiness Assessment

## Document Control
Organisational Readiness Assessment - Document Control For Better Care Victoria Use Only
Document Owner: | <insert>
Document Location: | <insert>
Document version
Version | Effective From | Effective To | Change Summary
<version # e.g. 0.1> | DD/MM/YY | DD/MM/YY | <insert title of draft version>
<version # e.g. 0.1> | DD/MM/YY | DD/MM/YY | <insert title of draft version>
<version # e.g. 0.1> | DD/MM/YY | DD/MM/YY | <insert title of draft version>
<version # e.g. 0.1> | DD/MM/YY | DD/MM/YY | <insert title of draft version>
<version # e.g. 0.1> | DD/MM/YY | DD/MM/YY | <insert title of draft version>
Document approval
Position / Title | Name | Signature | Date
<insert> | <insert>

## Guidelines
Organisational Readiness Assessment - Guidelines
What is an Organisational Readiness Assessment?
An Organisational Readiness Assessment is a process to review an organisations level of preparedness to undertake project activities and planned changes. When complete, the activity will highlight which areas of the organisation are likely to present challenges for project delivery.
What is the purpose of using this tool?
The purpose of this tool is to assist Project Leads in the early identification and understanding of which areas in the organisation require improvement or support to increase the likelihood of the project achieving it's desired outcomes. The assessment is presented in a survey-style which allows Project Leads to present their opinion on a number of different organisational readiness statements.
When should I use this tool?
Project Leads are to use this tool in 'Phase 2 - Business Case' to assess the organisations current capabilities and readiness to commence the project. This tool should again be used periodically in 'Phase 4 - Implementation' prior to significant change implementation to highlight any new issues which may impede on project activities. Finally, the tool can be used in 'Phase 5 - Project Close & Evaluation' to highlight any new issues which may arise when handing over project activities to business as usual. Note: Numerous people can be surveyed by copying the orange worksheet as many times as required to provide a response sheet for each person.
How do I use this tool?
Select the appropriate orange worksheet to match the stage of the project that you are currently in. Then proceed with the following steps.
1. The first statement requiring a response is 1.01 and can be found next to the 'Start Here' cell.
2. Review each statement and select the rating that best addresses each statement in the drop down box in column I. Use the 'key' at the top of the page to guide you in selecting the appropriate response.
3. If the rating is "Improvement Required" or "At Risk", briefly outline how you plan to improve this area or what support is required to change the rating to 'On Track'. Add these actions in the Project Schedule to assist with tracking progress.
4. Some questions have the option to further break down the information so users can specify the area requiring attention or is at risk.
Add these actions in the Project Schedule to assist with tracking progress.

## Phase 2 - Business Case
Organisational Readiness Assessment Check
[6 empty] | KEY | On track | Improvement Required | At Risk
|  |  | Complete | OVERALL ORGANISATIONAL READINESS ASSESSMENT PHASE 2 - BUSINESS CASE |  |  | The current organisational state is on target for achieving a state of organisational readiness in this area to support the project effectively. | There is potential for full program benefits not to be achieved without intervention. Opportunities exist to strengthen this area within the organisation to support project activities. | The current organisational state is likely to impact the successful outcome of the project. Significant work required in this area prior to the organisation undertaking project activities in this phase.
[7 empty] | N / A | Complete
[7 empty] | This section / question is not applicable to this project. Please provide a brief comment as to why it is not applicable. | Evidence can be provided to support the organisational readiness in this area and for the project to operate effectively.
1. People
| Is the organisation's people ready to support this phase of the project? |  |  |  | Rating |  | Comments <maximum 200 words> Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
| START HERE | 1.01 | Existing training programs including content, audiences, frequency and delivery mechanisms support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  |  |  | Specific the training program(s) if relevant | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 1.02 | The organisation has the right people with the right skills to be able to deliver the projects tasks within the proposed budget and to support the activities of the project within this phase. | The risks of not changing are clear and compelling to organisational members | Complete |  |  |  |  | 4
|  | 1.03 | Adequate organisational support and resources is available to support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  | 1.04 | There are strong advocates and champions for change to support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  | 1.05 | The leadership team been identified to guide the change effort within this project phase. |  | Complete |  |  |  |  | 4
|  | 1.06 | The stakeholders and those affected by the activities in this phase are supportive of the change process. |  | Complete |  |  |  |  | 4
2. Policy and Process
| Is the organisation's internal structure ready to support this phase of the project? |  |  |  | Rating |  | Comments Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
|  | 2.01 | The organisation's governance structure is set up to support the project activities within this phase. |  | Complete |  |  |  |  | 4
|  | 2.02 | Existing policies and procedures support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  |  |  | Specific the policies if relevant | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 2.03 | Existing business reporting processes support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  |  |  | Specific the business reporting processes if relevant | Please select |  |  |  |  | 0
|  |  |  | e.g. Existing process 2 | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 2.04 | The existing performance management framework such as KPIs and metrics support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  | 2.05 | The existing inventory processes such as those relating to consumables support the activities of the project in this phase. |  | Complete |  |  |  |  | 4
3. Infrastructure
| Is the organisation's infrastructure ready to support this phase of the project? |  |  |  | Rating |  | Comments Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
|  | 3.01 | There are sufficient existing IT systems to support the activities of the project in this phase. |  | Complete |  |  |  |  | 4
|  | 3.02 | The physical space is adequate and supports the activities of the project in this phase. |  | Complete |  |  |  |  | 4
[10 empty] | 52 | 13
4

## Phase 4 - Implementation
Organisational Readiness Assessment Check
[6 empty] | KEY | On track | Improvement Required | At Risk
|  |  | Improvement Required | OVERALL ORGANISATIONAL READINESS ASSESSMENT PHASE 4 - IMPLEMENTATION |  |  | The current organisational state is on target for achieving a state of organisational readiness in this area to support the project effectively. | There is potential for full program benefits not to be achieved without intervention. Opportunities exist to strengthen this area within the organisation to support project activities. | The current organisational state is likely to impact the successful outcome of the project. Significant work required in this area prior to the organisation undertaking project activities in this phase.
[7 empty] | N / A | Complete
[7 empty] | This section / question is not applicable to this project. Please provide a brief comment as to why it is not applicable. | Evidence can be provided to support the organisational readiness in this area and for the project to operate effectively.
1. People
| Is the organisation's people ready to support this phase of the project? |  |  |  | Rating |  | Comments <maximum 200 words> Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
| START HERE | 1.01 | Existing training programs including content, audiences, frequency and delivery mechanisms support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  |  |  | Specific the training program(s) if relevant | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 1.02 | The organisation has the right people with the right skills to be able to deliver the projects tasks within the proposed budget and to support the activities of the project within this phase. | The risks of not changing are clear and compelling to organisational members | N / A |  |  |  |  | 0
|  | 1.03 | Adequate organisational support and resources is available to support the activities of the project within this phase. |  | On Track |  |  |  |  | 1
|  | 1.04 | There are strong advocates and champions for change to support the activities of the project within this phase. |  | On Track |  |  |  |  | 1
|  | 1.05 | The leadership team been identified to guide the change effort within this project phase. |  | Improvement Required |  |  |  |  | 2
|  | 1.06 | The stakeholders and those affected by the activities in this phase are supportive of the change process. |  | Complete |  |  |  |  | 4
2. Policy and Process
| Is the organisation's internal structure ready to support this phase of the project? |  |  |  | Rating |  | Comments Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
|  | 2.01 | The organisation's governance structure is set up to support the project activities within this phase. |  | On track |  |  |  |  | 1
|  | 2.02 | Existing policies and procedures support the activities of the project within this phase. |  | On track |  |  |  |  | 1
|  |  |  | Specific the policies if relevant | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 2.03 | Existing business reporting processes support the activities of the project within this phase. |  | On track |  |  |  |  | 1
|  |  |  | Specific the business reporting processes if relevant | Please select |  |  |  |  | 0
|  |  |  | e.g. Existing process 2 | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 2.04 | The existing performance management framework such as KPIs and metrics support the activities of the project within this phase. |  | On track |  |  |  |  | 1
|  | 2.05 | The existing inventory processes such as those relating to consumables support the activities of the project in this phase. |  | On track |  |  |  |  | 1
3. Infrastructure
| Is the organisation's infrastructure ready to support this phase of the project? |  |  |  | Rating |  | Comments Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
|  | 3.01 | There are sufficient existing IT systems to support the activities of the project in this phase. |  | Complete |  |  |  |  | 4
|  | 3.02 | The physical space is adequate and supports the activities of the project in this phase. |  | Improvement Required |  |  |  |  | 2
[10 empty] | 23 | 13
1.7692

## Phase 5 - Close & Evaluation
Organisational Readiness Assessment Check
[6 empty] | KEY | On track | Improvement Required | At Risk
|  |  | Improvement Required | OVERALL ORGANISATIONAL READINESS ASSESSMENT PHASE 5 - PROJECT CLOSE & EVALUATION |  |  | The current organisational state is on target for achieving a state of organisational readiness in this area to support the project effectively. | There is potential for full program benefits not to be achieved without intervention. Opportunities exist to strengthen this area within the organisation to support project activities. | The current organisational state is likely to impact the successful outcome of the project. Significant work required in this area prior to the organisation undertaking project activities in this phase.
[7 empty] | N / A | Complete
[7 empty] | This section / question is not applicable to this project. Please provide a brief comment as to why it is not applicable. | Evidence can be provided to support the organisational readiness in this area and for the project to operate effectively.
1. People
| Is the organisation's people ready to support this phase of the project? |  |  |  | Rating |  | Comments <maximum 200 words> Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
| START HERE | 1.01 | Existing training programs including content, audiences, frequency and delivery mechanisms support the activities of the project within this phase. |  | Complete |  |  |  |  | 4
|  |  |  | Specific the training program(s) if relevant | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 1.02 | The organisation has the right people with the right skills to be able to deliver the projects tasks within the proposed budget and to support the activities of the project within this phase. | The risks of not changing are clear and compelling to organisational members | N / A |  |  |  |  | 0
|  | 1.03 | Adequate organisational support and resources is available to support the activities of the project within this phase. |  | On Track |  |  |  |  | 1
|  | 1.04 | There are strong advocates and champions for change to support the activities of the project within this phase. |  | On Track |  |  |  |  | 1
|  | 1.05 | The leadership team been identified to guide the change effort within this project phase. |  | Improvement Required |  |  |  |  | 2
|  | 1.06 | The stakeholders and those affected by the activities in this phase are supportive of the change process. |  | Complete |  |  |  |  | 4
2. Policy and Process
| Is the organisation's internal structure ready to support this phase of the project? |  |  |  | Rating |  | Comments Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
|  | 2.01 | The organisation's governance structure is set up to support the project activities within this phase. |  | On track |  |  |  |  | 1
|  | 2.02 | Existing policies and procedures support the activities of the project within this phase. |  | On track |  |  |  |  | 1
|  |  |  | Specific the policies if relevant | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 2.03 | Existing business reporting processes support the activities of the project within this phase. |  | On track |  |  |  |  | 1
|  |  |  | Specific the business reporting processes if relevant | Please select |  |  |  |  | 0
|  |  |  | e.g. Existing process 2 | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
[5 empty] | Please select |  |  |  |  | 0
|  | 2.04 | The existing performance management framework such as KPIs and metrics support the activities of the project within this phase. |  | On track |  |  |  |  | 1
|  | 2.05 | The existing inventory processes such as those relating to consumables support the activities of the project in this phase. |  | On track |  |  |  |  | 1
3. Infrastructure
| Is the organisation's infrastructure ready to support this phase of the project? |  |  |  | Rating |  | Comments Note: if the rating is "Improvement Required" or "At Risk", outline how you plan to improve this area or what support is required
|  | 3.01 | There are sufficient existing IT systems to support the activities of the project in this phase. |  | Complete |  |  |  |  | 4
|  | 3.02 | The physical space is adequate and supports the activities of the project in this phase. |  | Improvement Required |  |  |  |  | 2
[10 empty] | 23 | 13
1.7692

## Drop Down Inputs
Drop Down Options
Please select
On Track
Improvement Required
At Risk
Complete
N / A