## Report
Problem Solving Report: | [5 empty] | Unnecessary blood gases in 'ward ready' patients
Leader: |  |  | Vicky Jones
Team: |  |  | Yvette O'Brien, Emily Harman, Rachael Johnstone, David Reid, Clare Hammer
Date |  |  | Commenced: | 2018-05-31 |  |  |  | Latest Update: | 2018-10-17
| 1. Problem Statement | [8 empty] | PLAN |  | 5. Counter-measure (Future State) |  |  |  | PLAN
Current Performance:
The mean number of blood gases taken on "ward ready" patients in the DCCM is 166/mth
GAP:
60% of blood gases taken on "ward ready patients are deemed to add low or no value to patient care
Expected Performance:
The mean number of blood gases taken on "ward ready" patients in the DCCM is 66/mth
| 2. Current State | [8 empty] | PLAN
[12 empty] | 6. Implementation |  |  |  |  | DO
[12 empty] | Action |  |  | Responsible | Date |  | Status
[12 empty] | Liaise with other ICUs re: ward ready process |  |  | Vicky | 2018-08-24 |  | Completed
[12 empty] | Countermeasure development workshop |  |  | ICU staff | 2018-08-24 |  | Completed
[12 empty] | Develop 'ward ready' standard |  |  | Vicky & Yvette | 2018-08-31 |  | Completed
[12 empty] | Socialise with nursing & medical staff for feedback |  |  | Vicky | 2018-09-04 |  | Completed
[12 empty] | Education sessions |  |  | Vicky | 5-17/9/18 |  | Completed
[12 empty] | Ward ready standard trial |  |  | Vicky & Clare | 17-30/9/18 |  | Completed
[12 empty] | Review results |  |  | PWG | 2018-10-05 |  | Completed
[12 empty] | Modify countermeasure as required |  |  | PWG | 2018-10-26 |  | On track
[12 empty] | Check results |  |  | PWG | 2018-11-09 |  | On track
[12 empty] | Standardise new process |  |  | Vicky & Clare | 2018-11-30 |  | On track
Refined Problem Statement:
| 40% of patients in the DCCM require blood gas analysis once deemed ready for discharge. | [10 empty] | 7. Check Results |  |  |  | CHECK
| 3. Target Setting | [8 empty] | PLAN
|  | Primary Measures |  |  |  |  | Check Measures
|  | Measure |  | Current |  | Target | Measure |  |  | Current | Target
|  | Mean number of ABGs performed |  | 166/mth |  | 66/mth | Ward bed request cancellation |  |  | 31/mth | < 31/mth
[7 empty] | MET/Code Blue <24/24 |  |  | 2.2% | ≤2.2%
| 4. Root Cause Analysis | [8 empty] | PLAN
Key Outcomes:
Missed patient deterioration
DCCM Culture - "we have always done it this way"
[5 empty] | Fear of "getting into trouble" | [6 empty] | 8. Sustain & Spread |  |  |  | ACT
[5 empty] | Difficulty switching from DCCM to ward patient mind set | [7 empty] | How will the changes be sustained? | Where else could this apply?
Who owns decision of when to complete a blood gas?
WARD READY
NOT WARD READY